## Project Dashboard
HOME CONSTRUCTION COST PLAN — GROUND + FIRST FLOOR
Project / Owner | KSK | Village / District | Thuvar | Currency: INR (₹)
Built-up area (sq ft) | 2037 sq ft | Planned start date | 2026-11-20 | Fill yellow cells
Budget & Actual Summary
Cost Head | Budget / Estimate (₹) | Actual Paid (₹) | Variance (₹) | Notes
Materials | 32000 | 32000 | 0 | Material purchases and expenses
Labour & subcontractors | 0 | 0 | 0 | Use Daily Expenses for actuals by category
Engineer / architect / approvals | 200000 | 10000 | 190000 | Design, structural, supervision, approvals
Equipment / transport / misc. | 0 | 0 | 0 | Transport, tools, hire, waste, utilities
Contingency | 11600 |  |  | Calculated from base estimate
TOTAL | 243600 | 42000 | 201600 | Update the contingency % on Project Setup
Daily Expense |  | 42000 | 0
How to use
1. Start in Project Setup: enter contingency %, floors, target dates and notes.
2. Fill quantities and your local rates in Materials & BOQ, Labour & Work, Professional Fees, and Misc & Equipment.
3. Use Daily Expenses for date-wise payments/purchases. Enter each bill/payment as a separate row.
4. Use Quotation Compare to compare up to 4 vendors item-by-item before selecting a supplier.
5. Use Work Schedule to plan dates, responsible person, progress and dependencies for each construction activity.
6. Keep bills, measurement book, drawings and engineer-approved quantities as your source of truth.
See the 'Detailed Material List' sheet for separate rows for cement, steel, bricks/blocks, sand, aggregate, plumbing, electrical, tiles, paint, doors/windows and external works.
Note on C14: This is the total entered in Daily Expenses. Avoid counting the same bill again in the actual-paid columns on other sheets if you use this figure as your overall cash-outflow tracker.

## Project Setup
Setting | Value to fill | Notes
Project name / owner | KSK
Village / Panchayat / Taluk / District | Thuvar | Use full location for local rate quotes
Plot area (sq ft) | 2037
Ground floor built-up area (sq ft) | 1302
First floor built-up area (sq ft) | 735
Contingency % | 5% | Example 10%; adjust to your comfort
Planned start date | 2026-11-20
Target completion date
Soil test required? |  | Confirm with engineer
Water source / borewell | Available | Include separately if applicable
Septic tank / sewer connection |  | Include as applicable
EB service / temporary power |  | Include as applicable
Approvals / local body |  | Confirm current local requirements
Construction method / wall type | Brick | e.g. brick/AAC; engineer to specify
Roof type | RCC Slab | RCC slab / other
Notes / exclusions |  | Write items not included in estimate

## Detailed Material List Ground
S.No. | Floor / Area | Stage | Material / Item | Specification / Grade | Unit | Estimated Qty | Rate/ Qty (₹) | Wastage % | Estimated Cost (₹) | Supplier / Brand | Quote Ref | Order Date | Received Date | Qty Purchased | Actual Cost (₹) | Qty Balance | Notes
1 | Ground Floor | Site Prep | Site clearing / earthwork |  | cft
2 | Ground Floor | Foundation | Cement - OPC/PPC |  | bag
3 | Ground Floor | Foundation | M-sand / river sand (as specified) |  | unit
4 | Ground Floor | Foundation | 20 mm aggregate / jelly |  | unit
5 | Ground Floor | Foundation | 40 mm aggregate / jelly |  | unit
6 | Ground Floor | Foundation | TMT reinforcement steel bars |  | kg
7 | Ground Floor | Foundation | Binding wire |  | kg
8 | Ground Floor | Foundation | PCC / concrete |  | cum
9 | Ground Floor | Foundation | Shuttering / formwork |  | sq ft
10 | Ground Floor | Foundation | Anti-termite treatment |  | sq ft
11 | Ground Floor | Foundation | Waterproofing chemical |  | litre
12 | Ground Floor | Foundation | Foundation blocks / masonry |  | Nos
13 | Ground Floor | Plinth | Cement |  | bag
14 | Ground Floor | Plinth | M-sand / river sand |  | unit
15 | Ground Floor | Plinth | Aggregate / jelly |  | unit
16 | Ground Floor | Plinth | Filling soil / gravel |  | unit
17 | Ground Floor | Plinth | DPC / damp-proof material |  | sq ft
18 | Ground Floor | Structure | Cement - OPC/PPC |  | bag
19 | Ground Floor | Structure | TMT reinforcement steel bars |  | kg
20 | Ground Floor | Structure | Binding wire |  | kg
21 | Ground Floor | Structure | M-sand / river sand |  | unit
22 | Ground Floor | Structure | 20 mm aggregate / jelly |  | unit
23 | Ground Floor | Structure | Ready-mix concrete / site-mix concrete |  | cum
24 | Ground Floor | Structure | Shuttering plywood / plates |  | sq ft
25 | Ground Floor | Structure | Scaffolding hire / materials |  | day
26 | Ground Floor | Brickwork | Red bricks |  | Nos
27 | Ground Floor | Brickwork | Fly ash bricks (alternative) |  | Nos
28 | Ground Floor | Brickwork | AAC blocks (alternative) |  | Nos
29 | Ground Floor | Brickwork | Cement for masonry mortar |  | bag
30 | Ground Floor | Brickwork | M-sand / river sand for mortar |  | unit
31 | Ground Floor | Brickwork | Lintel reinforcement / concrete |  | lot
32 | Ground Floor | Roof Slab | Cement |  | bag
33 | Ground Floor | Roof Slab | TMT steel reinforcement |  | kg
34 | Ground Floor | Roof Slab | M-sand / river sand |  | unit
35 | Ground Floor | Roof Slab | 20 mm aggregate / jelly |  | unit
36 | Ground Floor | Roof Slab | Concrete / RMC |  | cum
37 | Ground Floor | Roof Slab | Roof waterproofing membrane / chemical |  | sq ft
38 | Ground Floor | Plastering | Cement |  | bag
39 | Ground Floor | Plastering | M-sand / plastering sand |  | unit
40 | Ground Floor | Plastering | Wall mesh / corner bead |  | running ft
41 | Ground Floor | Plumbing | PVC / CPVC / UPVC pipes by diameter |  | running ft
42 | Ground Floor | Plumbing | Pipe fittings, elbows, tees, valves |  | lot
43 | Ground Floor | Plumbing | Floor traps / nahani traps |  | Nos
44 | Ground Floor | Plumbing | Water tank |  | Nos
45 | Ground Floor | Plumbing | Water pump / motor |  | Nos
46 | Ground Floor | Plumbing | WC / toilet fittings |  | Nos
47 | Ground Floor | Plumbing | Wash basin |  | Nos
48 | Ground Floor | Plumbing | Kitchen sink |  | Nos
49 | Ground Floor | Plumbing | Taps / mixers / showers |  | Nos
50 | Ground Floor | Plumbing | Bathroom waterproofing |  | sq ft
51 | Ground Floor | Electrical | PVC conduit pipes |  | running ft
52 | Ground Floor | Electrical | Electrical wire - lighting circuit |  | m
53 | Ground Floor | Electrical | Electrical wire - power circuit |  | m
54 | Ground Floor | Electrical | Distribution board / MCB / RCCB |  | Nos
55 | Ground Floor | Electrical | Switches and sockets |  | Nos
56 | Ground Floor | Electrical | Switch boxes / junction boxes |  | Nos
57 | Ground Floor | Electrical | Earthing set / earth wire |  | lot
58 | Ground Floor | Electrical | Light fixtures / fans |  | Nos
59 | Ground Floor | Flooring | Floor tiles |  | sq ft
60 | Ground Floor | Flooring | Bathroom anti-skid tiles |  | sq ft
61 | Ground Floor | Flooring | Kitchen wall tiles / dado |  | sq ft
62 | Ground Floor | Flooring | Tile adhesive / cement mortar |  | bag
63 | Ground Floor | Flooring | Tile grout / spacers |  | kg
64 | Ground Floor | Doors & Windows | Main door and frame |  | set
65 | Ground Floor | Doors & Windows | Internal doors and frames |  | set
66 | Ground Floor | Doors & Windows | Bathroom doors |  | set
67 | Ground Floor | Doors & Windows | Windows / aluminium or UPVC |  | sq ft
68 | Ground Floor | Doors & Windows | Grills / safety bars |  | kg
69 | Ground Floor | Doors & Windows | Locks, hinges, handles and fittings |  | lot
70 | Ground Floor | Painting | Wall putty |  | kg
71 | Ground Floor | Painting | Interior primer |  | litre
72 | Ground Floor | Painting | Interior paint |  | litre
73 | Ground Floor | Painting | Exterior weatherproof paint |  | litre
74 | Ground Floor | Painting | Enamel / metal paint |  | litre
75 | Ground Floor | Painting | Brushes, rollers, sandpaper, consumables |  | lot
76 | Ground Floor | Kitchen | Kitchen counter stone |  | running ft
77 | Ground Floor | Kitchen | Kitchen sink fittings |  | lot
78 | Ground Floor | Kitchen | Kitchen cabinets (if planned) |  | running ft
79 | Ground Floor | Staircase | Staircase reinforcement steel |  | kg
80 | Ground Floor | Staircase | Cement / concrete |  | cum
81 | Ground Floor | Staircase | Stair tiles / stone |  | sq ft
82 | Ground Floor | External Works | Compound wall bricks / blocks |  | Nos
83 | Ground Floor | External Works | Compound wall steel / concrete |  | lot
84 | Ground Floor | External Works | Gate |  | Nos
85 | Ground Floor | External Works | Septic tank materials / tank |  | lot
86 | Ground Floor | External Works | Sewer / drainage pipes |  | running ft
87 | Ground Floor | External Works | Rainwater harvesting components |  | lot
88 | Ground Floor | External Works | Borewell / casing / pump |  | lot
89 | Ground Floor | External Works | Sump / overhead tank |  | lot
90 | Ground Floor | External Works | Paving blocks / outdoor tiles |  | sq ft
91 | Ground Floor | External Works | Outdoor drainage channels |  | running ft
92 | Ground Floor | External Works | Soil / gravel / landscaping |  | unit
93 | Ground Floor | General | Curing water / tanker |  | trip
94 | Ground Floor | General | Transport / unloading |  | trip
95 | Ground Floor | General | Nails, screws, cutting discs and consumables |  | lot
96 | Ground Floor | General | Site safety equipment |  | lot
97 | Ground Floor | General | Debris removal / cleaning |  | trip
Important: | This is a material checklist, not a measured quantity estimate. Fill quantities from engineer-approved drawings; choose only applicable alternatives and avoid double-counting.

## Detailed Material List First
S.No. | Floor / Area | Stage | Material / Item | Specification / Grade | Unit | Estimated Qty | Rate/ Qty (₹) | Wastage % | Estimated Cost (₹) | Supplier / Brand | Quote Ref | Order Date | Received Date | Qty Purchased | Actual Cost (₹) | Qty Balance | Notes
1 | Ground Floor | Structure | Cement - OPC/PPC |  | bag
2 | Ground Floor | Structure | TMT reinforcement steel bars |  | kg
3 | Ground Floor | Structure | Binding wire |  | kg
4 | Ground Floor | Structure | M-sand / river sand |  | unit
5 | Ground Floor | Structure | 20 mm aggregate / jelly |  | unit
6 | Ground Floor | Structure | Ready-mix concrete / site-mix concrete |  | cum
7 | Ground Floor | Structure | Shuttering plywood / plates |  | sq ft
8 | Ground Floor | Structure | Scaffolding hire / materials |  | day
9 | Ground Floor | Brickwork | Red bricks |  | Nos
10 | Ground Floor | Brickwork | Fly ash bricks (alternative) |  | Nos
11 | Ground Floor | Brickwork | AAC blocks (alternative) |  | Nos
12 | Ground Floor | Brickwork | Cement for masonry mortar |  | bag
13 | Ground Floor | Brickwork | M-sand / river sand for mortar |  | unit
14 | Ground Floor | Brickwork | Lintel reinforcement / concrete |  | lot
15 | Ground Floor | Roof Slab | Cement |  | bag
16 | First Floor | Roof Slab | TMT steel reinforcement |  | kg
17 | Ground Floor | Roof Slab | M-sand / river sand |  | unit
18 | Ground Floor | Roof Slab | 20 mm aggregate / jelly |  | unit
19 | Ground Floor | Roof Slab | Concrete / RMC |  | cum
20 | Ground Floor | Roof Slab | Roof waterproofing membrane / chemical |  | sq ft
21 | Ground Floor | Plastering | Cement |  | bag
22 | Ground Floor | Plastering | M-sand / plastering sand |  | unit
23 | Ground Floor | Plastering | Wall mesh / corner bead |  | running ft
24 | Ground Floor | Plumbing | PVC / CPVC / UPVC pipes by diameter |  | running ft
25 | Ground Floor | Plumbing | Pipe fittings, elbows, tees, valves |  | lot
26 | Ground Floor | Plumbing | Floor traps / nahani traps |  | Nos
27 | Ground Floor | Plumbing | Water tank |  | Nos
28 | Ground Floor | Plumbing | Water pump / motor |  | Nos
29 | Ground Floor | Plumbing | WC / toilet fittings |  | Nos
30 | Ground Floor | Plumbing | Wash basin |  | Nos
31 | Ground Floor | Plumbing | Kitchen sink |  | Nos
32 | Ground Floor | Plumbing | Taps / mixers / showers |  | Nos
33 | Ground Floor | Plumbing | Bathroom waterproofing |  | sq ft
34 | Ground Floor | Electrical | PVC conduit pipes |  | running ft
35 | Ground Floor | Electrical | Electrical wire - lighting circuit |  | m
36 | Ground Floor | Electrical | Electrical wire - power circuit |  | m
37 | Ground Floor | Electrical | Distribution board / MCB / RCCB |  | Nos
38 | Ground Floor | Electrical | Switches and sockets |  | Nos
39 | Ground Floor | Electrical | Switch boxes / junction boxes |  | Nos
40 | Ground Floor | Electrical | Earthing set / earth wire |  | lot
41 | Ground Floor | Electrical | Light fixtures / fans |  | Nos
42 | Ground Floor | Flooring | Floor tiles |  | sq ft
43 | Ground Floor | Flooring | Bathroom anti-skid tiles |  | sq ft
44 | Ground Floor | Flooring | Kitchen wall tiles / dado |  | sq ft
45 | Ground Floor | Flooring | Tile adhesive / cement mortar |  | bag
46 | Ground Floor | Flooring | Tile grout / spacers |  | kg
47 | Ground Floor | Doors & Windows | Main door and frame |  | set
48 | Ground Floor | Doors & Windows | Internal doors and frames |  | set
49 | Ground Floor | Doors & Windows | Bathroom doors |  | set
50 | Ground Floor | Doors & Windows | Windows / aluminium or UPVC |  | sq ft
51 | Ground Floor | Doors & Windows | Grills / safety bars |  | kg
52 | Ground Floor | Doors & Windows | Locks, hinges, handles and fittings |  | lot
53 | Ground Floor | Painting | Wall putty |  | kg
54 | Ground Floor | Painting | Interior primer |  | litre
55 | Ground Floor | Painting | Interior paint |  | litre
56 | Ground Floor | Painting | Exterior weatherproof paint |  | litre
57 | Ground Floor | Painting | Enamel / metal paint |  | litre
58 | Ground Floor | Painting | Brushes, rollers, sandpaper, consumables |  | lot
59 | Ground Floor | Kitchen | Kitchen counter stone |  | running ft
60 | Ground Floor | Kitchen | Kitchen sink fittings |  | lot
61 | Ground Floor | Kitchen | Kitchen cabinets (if planned) |  | running ft
62 | Ground Floor | Staircase | Staircase reinforcement steel |  | kg
63 | Ground Floor | Staircase | Cement / concrete |  | cum
64 | Ground Floor | Staircase | Stair tiles / stone |  | sq ft
65 | Ground Floor | External Works | Compound wall bricks / blocks |  | Nos
66 | Ground Floor | External Works | Compound wall steel / concrete |  | lot
67 | Ground Floor | External Works | Gate |  | Nos
68 | Ground Floor | External Works | Septic tank materials / tank |  | lot
69 | Ground Floor | External Works | Sewer / drainage pipes |  | running ft
70 | Ground Floor | External Works | Rainwater harvesting components |  | lot
71 | Ground Floor | External Works | Borewell / casing / pump |  | lot
72 | Ground Floor | External Works | Sump / overhead tank |  | lot
73 | Ground Floor | External Works | Paving blocks / outdoor tiles |  | sq ft
74 | Ground Floor | External Works | Outdoor drainage channels |  | running ft
75 | Ground Floor | External Works | Soil / gravel / landscaping |  | unit
76 | Ground Floor | General | Curing water / tanker |  | trip
77 | Ground Floor | General | Transport / unloading |  | trip
78 | Ground Floor | General | Nails, screws, cutting discs and consumables |  | lot
79 | Ground Floor | General | Site safety equipment |  | lot
80 | Ground Floor | General | Debris removal / cleaning |  | trip
Important: | This is a material checklist, not a measured quantity estimate. Fill quantities from engineer-approved drawings; choose only applicable alternatives and avoid double-counting.

## Materials & BOQ
Item ID | Floor / Area | Work Stage | Material / Item | Specification / Grade | Unit | Estimated Qty | Rate (₹/unit) | Wastage % | Estimated Amount (₹) | Supplier / Brand | Order Date | Qty Received | Qty Balance | Actual Amount (₹) | Notes
1 | Common/External | External Works | Red Sand | - | cft | 1 | 25000 | 0% | 25000 | - | 2026-09-01 | 1 | 0 | 25000 | Receipt 1
2 | Common/External | External Works | Red Sand | - | cft | 1 | 7000 | 0% | 7000 | - | 2026-09-04 | 1 | 0 | 7000 | Receipt 2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
Note on O1: Enter actual amount paid for this material line. The dashboard uses this column for material actuals.

## Labour & Work
Work ID | Floor / Area | Work Stage | Labour / Contractor Work | Unit | Planned Qty | Rate (₹/unit) | Estimated Amount (₹) | Contractor / Team | Start Date | End Date | Payment Mode | Amount Paid (₹) | Balance (₹) | Work Status | Notes

## Professional Fees
Fee ID | Service / Fee Head | Professional / Office | Scope / Deliverable | Agreed Fee (₹) | Estimated Total (₹) | Payment Details |  |  | Actual Paid (₹) | Balance (₹) | Due Date | Receipt
1 | Architect / plan preparation
2 | Site engineer / supervision | Mr | Structural design / drawings Survey / setting out Plumbing design Electrical design Quantity survey / estimation Supervision | 200000 | 200000 | Payment Date | Paid | Notes | 10000 | 190000
[6 empty] | 2026-10-30 | 10000 | Advance
3 | Approval / permit / local body fees
4 | Other professional fee

## Misc & Equipment
Item ID | Work Stage | Expense / Equipment | Unit | Qty | Rate (₹) | Estimated Amount (₹) | Actual Amount (₹) | Vendor | Date Needed | Notes
1 |  | JCB / excavator hire
2 |  | Concrete mixer / vibrator hire
3 |  | Scaffolding / shuttering hire
4 |  | Cement / sand transport
5 |  | Aggregate transport
6 |  | Water tanker
7 |  | Temporary electricity / generator
8 |  | Site security
9 |  | Debris removal / disposal
10 |  | Tools / consumables
11 |  | Borewell / pump
12 |  | Septic tank / soak pit
13 |  | Compound wall / gate
14 |  | Rainwater harvesting
15 |  | External paving / drainage
16 |  | Cleaning / handover
17 |  | Other

## Daily Expenses
Date | Bill / Voucher No. | Floor / Area | Work Stage | Expense Category | Item / Description | Vendor / Person | Amount Paid (₹) | Payment Mode | Paid By | Received by | Bill Received? | Notes
2026-09-01 | Receipt 1 | Common/External | Site Prep | Material | Red Sand | - | 25000 | UPI | Vengadesh | Kanakaraj | Yes
2026-09-04 | Receipt 2 | Common/External | Site Prep | Material | Red Sand | - | 7000 | UPI | Vengadesh | Kanakaraj | Yes
2026-10-30 | Receipt 3 | Common/External | External Works | Engineer/Architect | Engineer Advance payment | Mr Shanmugapandi | 10000 | Bank Transfer | Vengadesh | Shanmugapandi | Yes
Note on H1: Record each payment once. If the payment is also entered as an actual payment on another sheet, avoid adding both totals together in a combined total.

## Work Schedule
Activity ID | Floor / Area | Construction Activity | Planned Start | Planned Finish | Actual Start | Actual Finish | Duration (days) | Predecessor / Dependency | Responsible Person | Status | % Complete | Planned Budget (₹) | Actual Cost (₹) | Delay (days) | Notes
1 | Common/External | Site setup & setting out
2 | Ground Floor | Excavation
3 | Ground Floor | PCC / footing preparation
4 | Ground Floor | Footing reinforcement & concrete
5 | Ground Floor | Foundation / column up to plinth
6 | Ground Floor | Plinth beam & filling
7 | Ground Floor | Ground floor columns & beams
8 | Ground Floor | Ground floor slab / roof over GF
9 | First Floor | First floor masonry
10 | First Floor | First floor columns / beams (if applicable)
11 | First Floor | First floor roof slab
12 | Ground Floor | Brickwork / partitions
13 | Common/External | Plumbing rough-in
14 | Common/External | Electrical conduit rough-in
15 | Common/External | Door/window frames
16 | Common/External | Internal & external plaster
17 | Common/External | Waterproofing
18 | Common/External | Floor & wall tiling
19 | Common/External | Plumbing fixtures
20 | Common/External | Electrical wiring & fittings
21 | Common/External | Doors, windows & grills
22 | Common/External | Putty & painting
23 | Common/External | Septic / drainage / rainwater works
24 | Common/External | Compound wall / gate / external paving
25 | Common/External | Testing, snag list & handover

## Floor Summary
Cost Head | Ground Floor (₹) | First Floor (₹) | Common / External (₹) | Notes
Materials | 0 | 0 | 32000 | Based on floor/area in Materials & BOQ
Labour | 0 | 0 | 0 | Based on floor/area in Labour & Work
TOTAL | 0 | 0 | 32000 | Does not include fees and misc unless assigned elsewhere